## PR Front
| DAILY PRODUCTION REPORT | [14 empty] | Production Office:
2323 Beverly Blvd
[16 empty] | Los Angeles, CA 90057 | [16 empty] | DATE: | Monday September 19, 2016
Ph: 818-515-1969
[7 empty] | 1st Unit |  | 2nd Unit |  |  | Test |  |  | Rehearsal |  |  | Holidays |  |  | Re-Takes 1 |  |  | Re-Takes 2 |  |  | Re-Takes 3 |  |  | Total |  |  |  | Schedule
Days Scheduled: | [6 empty] | 30 |  | - |  |  | - |  |  | - |  |  | 1 |  |  | - |  |  | - |  |  | - |  |  | 31
Days Ahead:
Actual Days: | [6 empty] | 25 |  | - |  |  | - |  |  | - |  |  | 1 |  |  | - |  |  | - |  |  | - |  |  | 26
Days Behind:
Director: Adam | [11 empty] | Co-Prod: Bailey
Producers: Jason, Oren | [11 empty] | Line Prod/UPM: Rick | [20 empty] | START DATE: |  |  |  |  | 2016-08-15
Exec Prods: Brian, James | [21 empty] | Sch. Finish Date | [5 empty] | 2016-09-26 |  |  |  |  | Est. Finish Date: |  |  |  |  | 2016-09-26
SETS: | [21 empty] | LOCATION:
109 |  | INT RUN DOWN FARMHOUSE - FALLOUT SHELTER | [19 empty] | RSI Pomona
3530 Pomona Blvd.
110 |  | INT RUN DOWN FARMHOUSE - FALLOUT SHELTER/CELL | [19 empty] | Pomona, CA 91769
3530 Pomona Blvd.
99 |  | INT RUN DOWN FARMHOUSE - FALLOUT SHELTER
97 |  | INT RAINIER FARMHOUSE - HALLWAY
93 |  | INT RAINIER FARMHOUSE - LIVING ROOM
95 |  | INT RAINIER FARMHOUSE - KITCHEN
Crew Call: |  |  |  | 7A | [7 empty] | Shooting Call: |  |  |  |  | 8A |  |  |  |  | First Shot: |  |  |  | 8A | [5 empty] | Lunch: |  |  | 1P-1:30P
1st Shot After Meal: | [5 empty] | 2:11P |  |  |  | Dinner: |  |  | - |  |  |  |  | 1st Shot After Meal: | [6 empty] | - |  |  | Camera Wrap: |  |  |  | 7:15P |  |  | Last Out: |  |  | 8P
SCRIPT SCENES & PAGES | [15 empty] | MINUTES | [6 empty] | SET-UPS
[7 empty] | SCENES |  |  |  | PAGES |  |  |  |  | Previous: |  |  |  | 2:00:46 |  |  | Previous: |  |  | 782
Script | [6 empty] | 168 |  |  |  | 97.875 |  |  |  |  | Today: |  |  |  | 0:04 |  |  | Today: |  |  | 36
Revised (Added) | [6 empty] | - |  |  |  | - |  |  |  |  | Total: |  |  |  | 2:04 |  |  | Total: |  |  | 818
Revised (Omitted) | [6 empty] | - |  |  |  | - |  |  |  |  | Scenes Shot Today: 109, 110, 99
Taken Previous | [6 empty] | 119 |  |  |  | 82.25 | [22 empty] | SOUND ROLLS
Taken Today | [6 empty] | 3 |  |  |  | 2.375 |  |  |  |  | Scenes Partially Shot: | [17 empty] | Previous: |  |  | 24
Total to Date | [6 empty] | 122 |  |  |  | 84.625 |  |  |  |  | Scenes Scheduled But Not Shot: | [17 empty] | Today: |  |  | 1
To be Taken | [6 empty] | 46 |  |  |  | 13.25 |  |  |  |  | Scenes Shot But Not Scheduled: | [17 empty] | Total: |  |  | 25
Notes:
CAMERA MAGS
[8 empty] | CAMERA ROLL |  |  |  |  | CARDS USED | [5 empty] | - | [5 empty] | - | [5 empty] | GIGABYTES | [7 empty] | NOTES
A |  |  |  |  | PREVIOUS: |  |  | 420602 |  |  |  |  | 418 | [5 empty] | - | [5 empty] | - | [5 empty] | Previous: |  |  |  |  | 420602
CAM |  |  |  |  | TODAY: |  |  | 2352 |  |  |  |  | 18 | [5 empty] | - | [5 empty] | - | [5 empty] | Shot Today: |  |  |  |  | 2352
[5 empty] | TO DATE: |  |  | 422954 |  |  |  |  | 436 | [5 empty] | - | [5 empty] | - | [5 empty] | To Date: |  |  |  |  | 422954
|  | FILM USE | [5 empty] | PRINT |  |  |  |  | NO GOOD | [5 empty] | WASTE | [5 empty] | TOTAL | [5 empty] | Starting Inventory:
[5 empty] | PREVIOUS: | [25 empty] | Add'l Received:
[5 empty] | TODAY: | [25 empty] | Shot Today:
[5 empty] | TO DATE: | [25 empty] | Ending Inventory:
[8 empty] | CAMERA ROLL |  |  |  |  | MAGS USED | [5 empty] | - | [5 empty] | -
B |  |  |  |  | PREVIOUS: | [13 empty] | - | [5 empty] | -
CAM |  |  |  |  | TODAY: | [13 empty] | - | [5 empty] | -
[5 empty] | TO DATE: |  |  | 0 |  |  |  |  | 0 | [5 empty] | - | [5 empty] | -
[8 empty] | CAMERA ROLL |  |  |  |  | MAGS USED | [11 empty] | -
C |  |  |  |  | PREVIOUS: |  |  | 0 |  |  |  |  | 0 | [5 empty] | - | [5 empty] | -
CAM |  |  |  |  | TODAY: |  |  | 0 |  |  |  |  | 0 | [5 empty] | - | [5 empty] | -
[5 empty] | TO DATE: |  |  | 0 |  |  |  |  | 0 | [5 empty] | - | [5 empty] | -
NOTES:
CAST - WEEKLY & DAY PLAYERS | [13 empty] | N | MU/ |  |  | WORK TIME | [8 empty] | MEAL |  |  |  |  | TRAVEL TIME
S=Start H=Hold TR=Travel F=Finish W=Work D=Drop FT=Fitting | [13 empty] | D | WARD |  |  | REPORT |  |  | DISMISS |  |  | M/U |  |  | 1st |  | 2nd |  |  | ARRIVE |  |  | LEAVE |  |  | STUNT |  | MPV
# | CAST | [6 empty] | CHARACTER |  |  |  | STATUS |  | B | CALL |  |  | ON SET |  |  | ON SET |  |  | DISMISS |  |  | IN/OUT |  | IN/OUT |  |  | LOCATION |  |  | LOCATION |  |  | ADJ. / NOTES
1 | Linda | [6 empty] | LIZZY |  |  |  | W |  | X | 6A |  |  | 7A |  |  | 10:35A |  |  | 10:50A |  |  | - |  | - |  |  | - |  |  | - |  |  | - |  | -
2 | Lee | [6 empty] | BRONZE |  |  |  | W |  | X | 6:15A |  |  | 7A |  |  | 10:35A |  |  | 10:50A |  |  | - |  | - |  |  | - |  |  | - |  |  | - |  | -
3 | Andrew | [6 empty] | BRAD |  |  |  | W |  | X | 6:15A |  |  | 7A |  |  | 10:35A |  |  | 10:50A |  |  | - |  | - |  |  | - |  |  | - |  |  | - |  | -
4 | Kurt | [6 empty] | TREVOR |  |  |  | H |  | - | - |  |  | - |  |  | - |  |  | - |  |  | - |  | - |  |  | - |  |  | - |  |  | - |  | -
5 | Catherine | [6 empty] | AMY |  |  |  | W |  | X | 6A |  |  | 7A |  |  | 11:48A |  |  | 12:03P |  |  | - |  | - |  |  | - |  |  | - |  |  | - |  | -
6 | Susan | [6 empty] | MANDY |  |  |  | W |  | - | 7:20A |  |  | 7A |  |  | 7:15P |  |  | 7:30P |  |  | 1P-1:30P |  | - |  |  | - |  |  | - |  |  | - |  | -
7 | Jeremy | [6 empty] | DUPAR |  |  |  | H |  | - | - |  |  | - |  |  | - |  |  | - |  |  | - |  | - |  |  | - |  |  | - |  |  | - |  | -
8 | Teresa | [6 empty] | ADELE |  |  |  | H |  | - | - |  |  | - |  |  | - |  |  | - |  |  | - |  | - |  |  | - |  |  | - |  |  | - |  | -
9 | Alec | [6 empty] | MICHELLE |  |  |  | H |  | - | - |  |  | - |  |  | - |  |  | - |  |  | - |  | - |  |  | - |  |  | - |  |  | - |  | -
12 | Robert | [6 empty] | BRUCE |  |  |  | WF |  | X | 6:30A |  |  | 7A |  |  | 11:05A |  |  | 11:20A |  |  | - |  | - |  |  | - |  |  | - |  |  | - |  | -
13 | Julian | [6 empty] | FRENCH |  |  |  | W |  | - | 7:30A |  |  | 12P |  |  | 6:56P |  |  | 7:48P |  |  | 1P-1:30P |  | - |  |  | - |  |  | - |  |  | - |  | 0/1
20K | Hana Hayes | [6 empty] | TEENAGE ELISE |  |  |  | WF |  | - | 12:30P |  |  | 3:18P | [10 empty] | - |  |  | - |  |  | - |  |  | -
21K | Thomas Robie | [6 empty] | TEENAGE CHRISTIAN |  |  |  | PWF |  | - | 10:30A |  |  | 3:18P | [8 empty] | 12:30P-1P |  | - |  |  | - |  |  | - |  |  | - |  | -
100X | Bob | [6 empty] | STUNT COORDINATOR |  |  |  | W |  | X | - |  |  | 6A |  |  | 6P |  |  | - |  |  | 1P-1:30P |  | - |  |  | - |  |  | - |  |  | - |  | -
103AX | Nick King | [6 empty] | TUCKER STUNT DBL |  |  |  | SWF |  | X | 8A |  |  | 8:30A | [10 empty] | - |  |  | - |  |  | - |  |  | -
103AX | Nick King | [6 empty] | TUCKER STUNT DBL |  |  |  | SWF |  | X | 7:30A |  |  | 8:30A | [10 empty] | - |  |  | - |  |  | - |  |  | -
106X | Mac | [6 empty] | MANDY STUNT DBL |  |  |  | SWF |  | - | 8A |  |  | 11:40A |  |  | 5:04P |  |  | 5:19P |  |  | 1P-1:30P |  | - |  |  | - |  |  | - |  |  | 1400 |  | -
200X | Stephen | [6 empty] | UTILITY STUNT |  |  |  | SWF |  | X | - |  |  | 6A |  |  | 6P |  |  | - |  |  | 1P-1:30P |  | - |  |  | - |  |  | - |  |  | - |  | -
[29 empty] | - |  |  | - |  |  | - |  |  | -
201X | Peter | [6 empty] | UTILITY STUNT |  |  |  | SWF |  | X | - |  |  | 6A |  |  | 6P |  |  | - |  |  | 1P-1:30P |  | - |  |  | - |  |  | - |  |  | - |  | -
203X | Paul | [6 empty] | UTILITY STUNT |  |  |  | SWF |  | X | - |  |  | 6A |  |  | 6P |  |  | - |  |  | 1P-1:30P |  | - |  |  | - |  |  | - |  |  | - |  | -
X= | NDB: |  | 6:45A-7A
|  | EXTRA TALENT | [7 empty] | Union |  |  | 1 |  |  |  |  | Non-Union |  |  |  | 0 | [5 empty] | Stand-In |  | 4 | [5 empty] | Total |  | 5
# |  | RATE |  |  | CALL |  |  | DISMISS |  | MEAL |  |  |  | NDB |  | MPVS |  | ADJ |  |  |  | # |  | RATE |  |  | CALL |  | DISMISS |  |  | MEAL | [5 empty] | MPVS | ADJ
1 |  | $300/8 |  |  | 7A |  |  | 3:30P |  | 1P-1:30P |  |  |  | - |  | - |  | -
2 |  | $189/8 |  |  | 7A |  |  | 1P |  | - |  |  |  | - |  | - |  | M, S
1 |  | $189/8 |  |  | 7A |  |  | 7P |  | 1P-1:30P |  |  |  | - |  | - |  | M, S
1 |  | $189/8 |  |  | 7A |  |  | 7:20P |  | 1P-1:30P |  |  |  | - |  | - |  | M, S
1 |  | $75/2 |  |  | 2P |  |  | 6P |  | - |  |  |  | - |  | - |  | M
H = |  | WIG
S = |  | SMOKE
M = |  | 60 Miles
X = |  | NDB:
A.D.'S: Dan, Marc, Phil | [40 empty] | UNIT PRODUCTION MANAGER: Rick

## back
|  |  |  | DAILY PRODUCTION REPORT | [5 empty] | Day: | 25 | of | 30 |  |  | Monday September 19, 2016
NO | DEPARTMENT | MPV | NAME | CALL | WRAP | NO | DEPARTMENT | MPV | NAME | CALL | WRAP | NO | DEPARTMENT | MPV | NAME | CALL | WRAP
| PRODUCTION | [5 empty] | SPECIAL EFFECTS | [5 empty] | LOCATIONS
1 | Director | - | Adam | 7 | 19.3 | 1 | Special EFX Coord. |  | Steve | O/C | O/C | 1 | Location Manager | - | Kandice | O/C | O/C
1 | Writer | - | Lee | O/C | O/C |  | Special EFX Supervisor |  |  |  |  | 1 | Key Asst. Location Mgr | - | Nate | O/C | O/C
1 | Line Producer / U.P.M. | - | Rick | O/C | O/C | 1 | Special EFX Foreman |  | Zak | 7 | 19.7 | 1 | Key Asst. Location Mgr | - | Jim | O/C | O/C
1 | 1st Asst. Director | - | Dan | 7 | 19.3 | 1 | Special EFX Tech |  | Sean | 7 | 19.7 | 1 | Asst. Location Mgr | - | Erin | O/C | O/C
1 | 2nd Asst. Dir. | MM | Marc | 5.7 | 20.3 |  | Special EFX Tech
1 | 2nd 2nd Asst. Dir. | MM | Phil | 6.5 | 20.3 |  | Special EFX Tech
1 | DGA Trainee |  | Mindy | 5.7 | 20.1 |  | MAKE UP/HAIR |  |  |  |  | 1 | FSO
[6 empty] | 1 | Make-Up Dept. Head |  | Anthony | 5.7 | 18 | 1 | MRCA Ranger
1 | Set P.A. |  | Gary | 6 | 19.8 | 1 | Key Make-Up Artist |  | Carleigh | 5.7 | 19.7 | 3 | Security
1 | Set P.A. |  | Deandra | 6 | 20.1 | 1 | Add'l Make-Up |  | Adrienne Booth | 7.5 |  |  | Layout Board Techs |  | 'Bubbles'
| Set P.A. |  | Kyle Kruse | [9 empty] | CASTING
[12 empty] | 1 | Casting Director |  | Terri | O/C | O/C
[6 empty] | 1 | Hair Dept. Head |  | Yunea | 5.7 | 19.7 | 1 | Casting Associate |  | Sarah | O/C | O/C
[6 empty] | 1 | Key Hair Stylist |  | Enoch | 5.7 | 19.7 | 1 | Casting Assistant |  | Ally | O/C | O/C
[12 empty] | 1 | Extras Casting | - | Tyler | O/C | O/C
1 | Script Supervisor |  | Vanessa Meier | 7 | 20.3 | 1 | Dept Head SPFX M/U |  | Justin | O/C | O/C | 1 | Extras Casting | - | Christina | O/C | O/C
[6 empty] | 1 | Coord SPFX M/U |  | Mike | O/C | O/C
1 | Production Supervisor | - | Laura | O/C | O/C | 1 | SPFX MU |  | Kelly | 7 | 20
1 | Prod. Coordinator | - | Madison | O/C | O/C | 1 | SPFX MU |  | Ken | 7 | 20 |  | SET OPERATIONS / ADD'L LABOR
1 | Prod. Secretary | - | Chad | O/C | O/C | 1 | SPFX MU |  | Danielle | 7 | 20 | 1 | Set Medic |  | Lisa | 6 | 19.8
1 | Office Assistant | - | Vinny | O/C | O/C | 1 | Lens Tech |  | Bob | 10.5 | 16.7 | 1 | Construction Medic |  | Beverly | 6 | 18
[7 empty] | WARDROBE | [5 empty] | Rigging Medic
[6 empty] | 1 | Costume Designer |  | Lisa | O/C | O/C |  | Techno Tech
[6 empty] | 1 | Costume Supervisor |  | David | 5.7 | 19.5 |  | Techno Tech
1 | Asst. to Director | - | Chelsea | O/C | O/C | 1 | Set Costumer |  | Heather | 5.7 | 19.5 | 1 | AC Tech |  | John | 6.7 | 19.7
1 | Asst. to Jason | - | Olivia | O/C | O/C |  | Set Costumer | [5 empty] | Teacher/Welfare Worker
[7 empty] | Costumer | [5 empty] | TRANSPORTATION
[7 empty] | Add'l Costumer |  | Phil Maldonado |  |  | 1 | Transport Coordinator |  | Matt | O/C | O/C
[6 empty] | 1 | Costume PA |  | Nicholas | 5.7 | 19.5 | 1 | Transpo. Captain |  | Myles | O/C | O/C
| CAMERA | [5 empty] | ART DEPARTMENT | [5 empty] | Drivers |  | Christina | O/C | O/C
1 | Dir. of Photography |  | Toby | 7 | 19.4 | 1 | Prod. Designer |  | Melanie | O/C | O/C |  | Drivers |  | Steven | O/C | O/C
1 | A Camera Op. |  | Damian | 7 | 19.4 | 1 | Art Director |  | Hunter | O/C | O/C |  | Drivers |  | TBD
1 | 1st AC A Camera |  | Brian | 7 | 19.8 |  | Set Designer | [5 empty] | Drivers |  | TBD
1 | 2nd AC A Camera |  | Geoffrey | 7 | 19.8 | 1 | Art Dept. Coord. |  | Zak | O/C | O/C |  | Drivers |  | TBD | A
1 | B Camera Op. |  | Denson | 7 | 19 | 1 | Art Dept. Assistant |  | Sarah | O/C | O/C |  | Drivers |  | Paul Ciancetta | L
1 | 1st AC B Camera |  | Christine | 7 | 19.3 | [6 empty] | 1 | Camera 10 Truck |  |  | L
1 | 2nd AC B Camera |  | Lani | 7 | 19.8 | [6 empty] | 1 | Grip Truck
1 | Digital Utility |  | Jose | 7 | 19.9 | [6 empty] | 1 | Electric Truck |  |  | C
1 | DIT |  | Oliver | 7 | 19.8 |  | CONSTRUCTION |  |  |  |  | 1 | Prop 10 Truck |  |  | A
[6 empty] | 1 | Construction Coord. |  | Drew | O/C | O/C | 1 | M/U-Hair Trailer |  |  | L
[6 empty] | 1 | General Foreman |  | Casey | O/C | O/C | 1 | Prod Van/Wardrobe Trailer |  | Paul | L
1 | Still Photographer |  | Justin | 8 | 18.5 |  | Construction PA |  |  |  |  | 1 | Honeywagon |  | Jon | S
[7 empty] | Laborers |  |  |  |  | 1 | Prod Motorhome
| VIDEO PLAYBACK |  |  |  |  | 1 | Lead Paint |  | Bob | O/C | O/C | 1 | Craft Service Trailer |  |  | P
1 | Video Assist |  | Chris | 7 | 19.7 | 1 | Propmaker |  | Sergio | O/C | O/C | 1 | Fuel Truck |  |  | E
[6 empty] | 1 | Construction |  | John | O/C | O/C |  | SPFX Trailer |  |  | R
| ELECTRIC | [11 empty] | 2 Room Trailer
1 | CLT |  | Kevin | 7 | 19.6 |  | Greensman | [5 empty] | 3 Room Trailer |  |  | C
1 | Best Boy Elec |  | Eric | 6.7 | 19.6 | 1 | Standby Painter |  | Joey | 7 | 19.7 |  | Grip Rigging Truck |  |  | O
1 | Set Lighting Tech. |  | Jon | 6.7 | 19.6 |  | SET DECORATION | [5 empty] | Set Dec. Trucks |  |  | O
1 | Set Lighting Tech. |  | Mike | 7 | 19.6 | 1 | Set Decorator |  | Sandy | O/C | O/C |  | Construction Stakebed |  |  | R
1 | Set Lighting Tech. |  | Zach | 7 | 19.6 | 1 | Leadperson |  | Devin | O/C | O/C |  | Electric Rigging Truck |  |  | D
1 | Add'l Lighting Tech |  | Dustin | 7 | 19.6 | 1 | Buyer |  | Erin | O/C | O/C
| Add'l Lighting Tech |  |  | 8 |  | 1 | Set Dresser |  | Tim | O/C | O/C | * | PICTURE CARS
| Add'l Lighting Tech |  | Robert Redner | 6.5 |  | 1 | Set Dresser |  | Darren | O/C | O/C | 1 | Spectral Sightings Bus |  | 50's Coroner Van
1 | Add'l Lighting Tech | [10 empty] | 1 | Gerald's Truck (1953) |  | Debend Cop cars
1 | Rigging Gaffer (Stage) |  | Kevin | 7 |  | 1 | On Set Dresser |  | Justin | 7 | 19.7 | 1 | 50's Coroner Van |  | Gerald's Truck (1953)
1 | Rigging Best Boy (Stage) |  | Ray | 7 |  |  | PROPERTY | [5 empty] | Garza's Truck |  | Ambulance #2 (+Gurney)
1 | Rigging Tech (Stage) |  | Chris | 7 |  | 1 | Property Master |  | Gary | 7 | 19.7
1 | Rigging Tech (Stage) |  | Ari | 7 |  | 1 | Asst. Prop Master |  | Curtis | 7 | 19.7
| GRIP | [5 empty] | Asst. Prop Master |  | Albert Valdez |  |  | * | SPECIAL EQUIPMENT
1 | Key Grip |  | Eric | 7 | 19.7 |  | Prop Assistant |  |  |  |  | 2 | 80' Lighting Condors
1 | Best Boy Grip |  | Cole | 7 | 19.7 |  | VISUAL EFFECTS |  |  |  |  | 1 | 45' Techno Crane
1 | "A" Camera Dolly Grip |  | Dave | 7 | 19.7 | 1 | VFX Producer |  | Jamison | 11 | 17.5 | 1 | Grip Cart
1 | Grip |  | John | 7 | 19.7 |  | VFX Supervisor
1 | Grip |  | Micah | 7 | 19.7 | [7 empty] | CRAFT SERVICE
1 | Grip |  | Charlie | 7 | 19.7 | [6 empty] | 1 | Craft Service |  | Luis | 6.5 | 20.3
1 | Add'l Grip |  | Galen Green | 8 |  |  | EDITORIAL |  |  |  |  | 1 | Asst. Craft Svc. |  | Victor | 7 | 20.3
1 | Add'l Grip |  | Mark Parsons | 8 |  | 1 | Editor |  | Tim | O/C | O/C
| Add'l Grip |  |  |  |  | 1 | 1st Asst Editor |  | Drew | O/C | O/C |  | CATERING
1 | Add'l Grip |  | Chris Barns | 13.5 |  |  | 2nd Asst Editor | [5 empty] | Hot Breakfast |  | Ready To Serve At: |  | 5.5
1 | Rigging Key (Stage) |  | Rick | 7 | 18 | [6 empty] | 113 | Total Hot Lunches Served |  | Ready To Serve Transpo At: |  | 12.5
1 | Rigging Best Boy (Stage) |  | Mark | 7 | 18 | [9 empty] | Ready To Serve Crew At: |  | 13
1 | Rigger (Stage) |  | James | 7 | 18 | [9 empty] | Ready to Serve BG At: |  | -
| SOUND | [5 empty] | ACCOUNTING
1 | Sound Mixer |  | Robert | 7 | 19.7 | 1 | Prod. Accountant |  | Justin | O/C | O/C
1 | Boom Operator |  | Jeff | 7 | 19.7 |  | 1st Asst. Accountant |  |  |  |  | 1 | Chef |  | Orlando | 1.5 | 18.5
1 | Sound Utility |  | Michael | 7 | 19.7 | [6 empty] | 1 | Asst. Chefs |  | Moises | 1.5 | 18.5
[6 empty] | 1 | Payroll Accountant |  | Bryan | O/C | O/C | 1 | Asst. Chefs |  | Franciscos | 1.5 | 18.5
80 | Walkies |  | Per Prod. |  |  | 1 | Payroll Clerk |  | Andy | O/C | O/C | 1 | Add'l Chef Assistant |  | Luis | 1.5 | 18.5
1) | Safety Meeting and evacuation plan held at crew call by Dan (1st AD).
2) | Mileage: 60 Miles
1 | SAFETY MEETING:
3) | DGA Meal Money to: Marc (2nd AD), Phil (2nd 2nd AD)
4) | DGA Wrap Supervision Allowance to Phil (2nd 2nd AD).
5) | SCHOOL:
6) | VARIED LUNCH:
7) | RERATES:
8) | NDB: Jose (A/C Tech)
9) | At 4:40P, Dan (1st AD) held a safety meeting regarding stunt work for Sc 99
10) | Julian (SAG) had an extended makeup dismissal due to SPFX makeup removal.
11) | 'B' camera wrapped early at 6:57P.
12) | A walking second meal was served at 7P to cast and crew.
DGA Meal Money to: D. Lazarovits (1st AD), M. Newland (2nd AD), P. DeSanti (2nd 2nd AD)
*** SEE MAP FOR NEAREST HOSPITAL INFORMATION ***

## Exhibit G
[8 empty] | SAG-AFTRA PERFORMERS PRODUCTION TIME REPORT | [20 empty] | Exhibit G
Picture Title | FALLOUT | [27 empty] | PAGE 1 OF 2
Company | FALLOUT SHELTER FILM LLC |  |  |  |  | Prod No. |  | Date | MONDAY, SEPTEMBER 19th 2016 | [6 empty] | Contact |  | LAURA ALTMANN | [7 empty] | Phone No. |  | 773 454 3462 |  | ROUND TRIP MILES
Shooting Location |  | LOS ANGELES |  |  |  | Is Today a Designated Day off?* |  |  | Yes | No | X |  | Production Type: |  |  | MP | X | TV |  |  | MOW |  | Industrial |  |  | Other
W = Work | R = Rehearsal |  | TR = Travel | FT = Fitting |  |  | WORK TIME
S = Start | H = Hold |  | T = Test | F = Finish |  | Report | Report | Dismiss | Dismiss |  |  | MEALS | [5 empty] | TRAVEL TIME |  |  |  |  | Minors | No. of |  |  |  |  | PERFORMER'S
|  | ROLE |  |  |  | Makeup/ | on | on | Makeup/ | ND Meal |  |  | 1st Meal |  | 2nd Meal |  | Leave for | Arrive on | Leave | Leave | Arrive at | Stunt | Tutoring | Outfits |  | Forced |  | MPVs | SIGNATURE
CAST |  | No. / Minor | CHARACTER |  |  | Wardrobe | Set | Set | Wardrobe | In | Out |  | Start | Finish | Start | Finish | Location | Location | Location | Location | Hotel | Adjustment | Time | Provided |  | Call | MPVs | MPVs
LIN SHAYE |  | 1 | ELISE RAINIER |  | W | 6A | 7A | 10:35A | 10:50A | 6:45A | 7A |  | - | - | - | - | - | - | - |  | - | - | - | - |  | - |  |  | 1
LEIGH WHANNELL |  | 2 | SPECS |  | W | 6:15A | 7A | 10:35A | 10:50A | 6:45A | 7A |  | - | - | - | - | - | - | - |  | - | - | - | - |  | - |  |  | 2
ANGUS SAMPSON |  | 3 | TUCKER |  | W | 6:15A | 7A | 10:35A | 10:50A | 6:45A | 7A |  | - | - | - | - | - | - | - |  | - | - | - | - |  | - |  |  | 3
KIRK ACEVEDO |  | 4 | TED GARZA |  | H | - | - | - | - | - | - |  | - | - | - | - | - | - | - |  | - | - | - | - |  | - |  |  | 4
CAITLIN GERARD |  | 5 | IMOGEN RAINIER |  | W | 6A | 7A |  |  | 6:45A | 7A |  | - | - | - | - | - | - | - |  | - | - | - | - |  | - |  |  | 5
SPENCER LOCKE |  | 6 | MELISSA RAINIER |  | W | 7:20A | 7A |  |  | - | - |  |  |  | - | - | - | - | - |  | - | - | - | - |  | - |  |  | 6
JOSH STEWART |  | 7 | GERALD RAINIER |  | H | - | - | - | - | - | - |  | - | - | - | - | - | - | - |  | - | - | - | - |  | - |  |  | 7
TESSA FERRER |  | 8 | AUDREY RAINIER |  | H | - | - | - | - | - | - |  | - | - | - | - | - | - | - |  | - | - | - | - |  | - |  |  | 8
ALEQUE REID |  | 9 | ANNA |  | H | - | - | - | - | - | - |  | - | - | - | - | - | - | - |  | - | - | - | - |  | - |  |  | 9
BRUCE DAVISON |  | 12 | CHRISTIAN RAINIER |  | WF | 6:30A | 7A |  |  | 6:45A | 7A |  | - | - | - | - | - | - | - |  | - | - | - | - |  | - |  |  | 12
AVA KOLKER |  | 10K | YOUNG ELISE |  | W | 11:30A |  |  |  | - | - |  |  |  | - | - | - | - | - |  | - | - | - | - |  | - |  |  | 10K
JAVIER BOTET |  | 13 | KEY FACED MAN |  | W | 7:30A |  |  |  | - | - |  |  |  | - | - | - | - | - |  | - | - | - | - |  | - |  |  | 13
ROB KING |  | 100X | STUNT COORDINATOR |  | W | - | 6A |  | - | 6:45A | 7A |  |  |  | - | - | - | - | - |  | - | - | - | - |  | - |  |  | 100X
CASSANDRA MCCORMICK |  | 106X | MELISSA STUNT DBL |  | SWF | 8A | 10:40A |  | - | - | - |  |  |  | - | - | - | - | - |  | - |  | - | - |  | - |  |  | 106X
CRAIG JENSEN |  | 200X | UTILITY STUNT |  | SWF | - | 6A |  | - | 6:45A | 7A |  |  |  | - | - | - | - | - |  | - |  | - | - |  | - |  |  | 200X
NICK BRETT |  | 201X | UTILITY STUNT |  | SWF | - | 6A |  | - | 6:45A | 7A |  |  |  | - | - | - | - | - |  | - |  | - | - |  | - |  |  | 201X
NICK KING |  | 203X | UTILITY STUNT |  | SWF | - | 6A |  | - | 6:45A | 7A |  |  |  | - | - | - | - | - |  | - |  | - | - |  | - |  |  | 203X
COLE MCKAY |  | 103X | TUCKER STUNT DBL |  | SWF | 7A | 8A |  |  | 7:45A | 8A |  |  |  | - | - | - | - | - |  | - | - | - | - |  | - |  |  | 103X
MARK A. WAGNER |  | 101 | STUNT PEE-WEE |  | SWF | 6A | 7A |  |  | 645A | 7A |  | 1206P | 1236P | - | - | - | - | - |  | - | - | - | - |  | -
JULIANA POTTER |  | 121 | STUNT MRS. ROSE |  | SWF | 530A | 720A |  |  | 645A | 7A |  | 1206P | 1236P | - | - | - | - | - |  | - | - | - | - |  | -
ALICE RIETVELD |  | 103 | STUNT BELLA |  | SWF | 7A | 940A |  |  | - | - |  |  |  | - | - | - | - | - |  | - | - | - | - |  | -
MARILYN GIACOMAZZI |  | 104 | STUNT PEPPER |  | SWF | 7A | 940A |  |  | - | - |  |  |  | - | - | - | - | - |  | - | - | - | - |  | -
GEORGINA RAWLINGS |  | 105A | STUNT FRECKLES |  | SWF | 7A | 940A |  |  | - | - |  |  |  | - | - | - | - | - |  | - | - | - | - |  | -
JESS KING |  | 200 | STUNT UTILITY - RIGGING |  | SWF | - | 6A |  | - | 645A | 7A |  | 1206P | 1236P | - | - | - | - | - |  | - | - | - | - |  | -
DAVE SCHULTZ |  | 203 | STUNT UTILITY - RIGGING |  | W | - | 6A |  | - | 645A | 7A |  | 1206P | 1236P | - | - | - | - | - |  | - | - | - | - |  | -
SHAWN ROBINSON |  | 204 | STUNT UTILITY - RIGGING |  | SWF | - | 6A |  | - | 645A | 7A |  | 1206P | 1236P | - | - | - | - | - |  | - | - | - | - |  | -
MARK RAYNER |  | 100X | STUNT COORDINATOR |  | W | [18 empty] | - |  | -
MARK A. WAGNER |  | 101 | STUNT PEE-WEE |  | SWF | [18 empty] | - |  | -
* This refers to the two (2) days (one (1) day on overnight location) which Producer can designate as day(s) off for the production for which performers are not paid continuous employment | [24 empty] | (UPM) |  |  |  | (AD)
16 rows for actors on legal
LIN SHAYE |  | 1 | ELISE RAINIER
Leigh Whannell |  | 2 | SPECS
Angus Sampson |  | 3 | TUCKER
Kirk Acevedo |  | 4 | TED GARZA
Caitlin Gerard |  | 5 | IMOGEN RAINIER
Spencer Locke |  | 6 | MELISSA RAINIER
Josh Stewart |  | 7 | GERARD RAINIER
Tess Ferrer |  | 8 | AUDREY RAINIER
ALEQUE REID |  | 9 | ANNA
Ava Kolker (9.8) |  | 10K | YOUNG ELISE
Pierce Pope |  | 11K | YOUNG CHRISTIAN
Bruce Davison |  | 12 | CHRISTIAN RAINIER
Javier Botet |  | 13 | KEY FACED MAN
Marcus Henderson |  | 14 | DETECTIVE WHITFIELD
|  | 15 | KEY FACED MAN - DOUBLE
AMANDA JAROS |  | 16 | MARA JENNINGS
OMIT |  | 17 | OMIT
Judith Drake |  | 18 | WAITRESS PAM
OMIT |  | 19 | OMIT
Hana Hayes |  | 20K | TEENAGE ELISE (16)
Thomas Robie |  | 21K | TEENAGE CHRISTIAN (12)
Josh Wingate |  | 22 | EXECUTED MAN (WAYNE FISHER)
|  | 23 | KITCHEN WOMEN
ROB KING |  | 100 | STUNT COORDINATOR
|  | 101 | STUNT DBL ELISE
|  | 102 | STUNT DBL SPECS
|  | 111 | STUNT DBL
|  | 112 | STUNT DBL
OMIT |  | 131 | STUNT DBL
|  | 200 | STUNT COP
|  | 201 | ND STUNT DRIVER #1
|  | 202 | ND STUNT DRIVER #2
|  | 203 | ND STUNT DRIVER #3
OMIT |  | 204 | STUNT FEMALE SHOPPER
|  | 210 | HELECOPTER PILOT
|  | 211 | HELECOPTER CREW
|  | XX | UTILITY STUNT - RIGGER
GREG BURNETT
TARA MACKEN
JESS KING |  |  | STUNT UTILITY - RIGGING
RILEY HARPER |  |  | STUNT WATER SAFETY
DAVE SCHULTZ |  |  | UTILITY STUNT - RIGGER
SHAWN ROBINSON |  |  | UTILITY STUNT - RIGGER
JAKE LOMBARD |  |  | UTILITY STUNT - RIGGER
MARK GINTHER |  |  | UTILITY STUNT - RIGGER
RAY SIEGLE |  |  | UTILITY STUNT - WATER SAFETY
MARK A. WAGNER |  |  | STUNT WATER SAFETY
JULIANA POTTER
JOE BUCCURO
OLIVER KELLER
DAVID CASTILLO
ALICE RIETVELD
MARILYN GIACOMAZ
WHITNEY COLEMAN
GEORGINA RAWLINGS
GEORGE COTTLE
JULIANA POTTER
BEVIN KAYE
KIMBERLY SHANNON MURPHY
JOEY BOX
NASH EDGERTON
JEREMY FRY
SETH DUHAMe
KATE BOYER
ALICE RIETVELD
EMILY BROBST
ZACK DUHAME
DALTON RONDELL
DAVID SCHULTZ
THOMAS STRUTHERS
MATT LEONARD

## Exhibit G Pg 2
[8 empty] | SAG-AFTRA PERFORMERS PRODUCTION TIME REPORT | [20 empty] | Exhibit G
Picture Title | FALLOUT | [27 empty] | PAGE 1 OF 2
Company | FALLOUT SHELTER FILM LLC |  |  |  |  | Prod No. |  | Date | THURSDAY, SEPTEMBER 15th 2016 | [6 empty] | Contact |  | LAURA ALTMANN | [7 empty] | Phone No. |  | 773 454 3462 |  | ROUND TRIP MILES
Shooting Location |  | LOS ANGELES |  |  |  | Is Today a Designated Day off?* |  |  | Yes | No | X |  | Production Type: |  |  | MP | X | TV |  |  | MOW |  | Industrial |  |  | Other
W = Work | R = Rehearsal |  | TR = Travel | FT = Fitting |  |  | WORK TIME
S = Start | H = Hold |  | T = Test | F = Finish |  | Report | Report | Dismiss | Dismiss |  |  | MEALS | [5 empty] | TRAVEL TIME |  |  |  |  | Minors | No. of |  |  |  |  | PERFORMER'S
|  | ROLE |  |  |  | Makeup/ | on | on | Makeup/ | ND Meal |  |  | 1st Meal |  | 2nd Meal |  | Leave for | Arrive on | Leave | Leave | Arrive at | Stunt | Tutoring | Outfits |  | Forced |  | MPVs | SIGNATURE
CAST |  | No. / Minor | CHARACTER |  |  | Wardrobe | Set | Set | Wardrobe | In | Out |  | Start | Finish | Start | Finish | Location | Location | Location | Location | Hotel | Adjustment | Time | Provided |  | Call | MPVs | MPVs
NICK BRETT |  | 201X | UTILITY STUNT |  | SWF | - | 8A |  | - | - | - |  |  |  | - | - | - | - | - |  | - |  | - | - |  | - |  |  | 201X
COLE MCKAY |  | 103X | TUCKER STUNT DBL |  | SWF | 7A | 8A |  |  | 7:45A | 8A |  |  |  | - | - | - | - | - |  | - | - | - | - |  | - |  |  | 103X
MARK A. WAGNER |  | 101 | STUNT PEE-WEE |  | SWF | 6A | 7A |  |  | 645A | 7A |  | 1206P | 1236P | - | - | - | - | - |  | - | - | - | - |  | -
JULIANA POTTER |  | 121 | STUNT MRS. ROSE |  | SWF | 530A | 720A |  |  | 645A | 7A |  | 1206P | 1236P | - | - | - | - | - |  | - | - | - | - |  | -
ALICE RIETVELD |  | 103 | STUNT BELLA |  | SWF | 7A | 940A |  |  | - | - |  |  |  | - | - | - | - | - |  | - | - | - | - |  | -
MARILYN GIACOMAZZI |  | 104 | STUNT PEPPER |  | SWF | 7A | 940A |  |  | - | - |  |  |  | - | - | - | - | - |  | - | - | - | - |  | -
GEORGINA RAWLINGS |  | 105A | STUNT FRECKLES |  | SWF | 7A | 940A |  |  | - | - |  |  |  | - | - | - | - | - |  | - | - | - | - |  | -
JESS KING |  | 200 | STUNT UTILITY - RIGGING |  | SWF | - | 6A |  | - | 645A | 7A |  | 1206P | 1236P | - | - | - | - | - |  | - | - | - | - |  | -
DAVE SCHULTZ |  | 203 | STUNT UTILITY - RIGGING |  | W | - | 6A |  | - | 645A | 7A |  | 1206P | 1236P | - | - | - | - | - |  | - | - | - | - |  | -
SHAWN ROBINSON |  | 204 | STUNT UTILITY - RIGGING |  | SWF | - | 6A |  | - | 645A | 7A |  | 1206P | 1236P | - | - | - | - | - |  | - | - | - | - |  | -
MARK RAYNER |  | 100X | STUNT COORDINATOR |  | W | [18 empty] | - |  | -
MARK A. WAGNER |  | 101 | STUNT PEE-WEE |  | SWF | [18 empty] | - |  | -
* This refers to the two (2) days (one (1) day on overnight location) which Producer can designate as day(s) off for the production for which performers are not paid continuous employment | [24 empty] | (UPM) |  |  |  | (AD)
16 rows for actors on legal
LIN SHAYE |  | 1 | ELISE RAINIER
Leigh Whannell |  | 2 | SPECS
Angus Sampson |  | 3 | TUCKER
Kirk Acevedo |  | 4 | TED GARZA
Caitlin Gerard |  | 5 | IMOGEN RAINIER
Spencer Locke |  | 6 | MELISSA RAINIER
Josh Stewart |  | 7 | GERARD RAINIER
Tess Ferrer |  | 8 | AUDREY RAINIER
ALEQUE REID |  | 9 | ANNA
Ava Kolker (9.8) |  | 10K | YOUNG ELISE
Pierce Pope |  | 11K | YOUNG CHRISTIAN
Bruce Davison |  | 12 | CHRISTIAN RAINIER
Javier Botet |  | 13 | KEY FACED MAN
Marcus Henderson |  | 14 | DETECTIVE WHITFIELD
|  | 15 | KEY FACED MAN - DOUBLE
AMANDA JAROS |  | 16 | MARA JENNINGS
OMIT |  | 17 | OMIT
Judith Drake |  | 18 | WAITRESS PAM
OMIT |  | 19 | OMIT
Hana Hayes |  | 20K | TEENAGE ELISE (16)
Thomas Robie |  | 21K | TEENAGE CHRISTIAN (12)
Josh Wingate |  | 22 | EXECUTED MAN (WAYNE FISHER)
|  | 23 | KITCHEN WOMEN
ROB KING |  | 100 | STUNT COORDINATOR
|  | 101 | STUNT DBL ELISE
|  | 102 | STUNT DBL SPECS
|  | 111 | STUNT DBL
|  | 112 | STUNT DBL
OMIT |  | 131 | STUNT DBL
|  | 200 | STUNT COP
|  | 201 | ND STUNT DRIVER #1
|  | 202 | ND STUNT DRIVER #2
|  | 203 | ND STUNT DRIVER #3
OMIT |  | 204 | STUNT FEMALE SHOPPER
|  | 210 | HELECOPTER PILOT
|  | 211 | HELECOPTER CREW
|  | XX | UTILITY STUNT - RIGGER
GREG BURNETT
TARA MACKEN
JESS KING |  |  | STUNT UTILITY - RIGGING
RILEY HARPER |  |  | STUNT WATER SAFETY
DAVE SCHULTZ |  |  | UTILITY STUNT - RIGGER
SHAWN ROBINSON |  |  | UTILITY STUNT - RIGGER
JAKE LOMBARD |  |  | UTILITY STUNT - RIGGER
MARK GINTHER |  |  | UTILITY STUNT - RIGGER
RAY SIEGLE |  |  | UTILITY STUNT - WATER SAFETY
MARK A. WAGNER |  |  | STUNT WATER SAFETY
JULIANA POTTER
JOE BUCCURO
OLIVER KELLER
DAVID CASTILLO
ALICE RIETVELD
MARILYN GIACOMAZ
WHITNEY COLEMAN
GEORGINA RAWLINGS
GEORGE COTTLE
JULIANA POTTER
BEVIN KAYE
KIMBERLY SHANNON MURPHY
JOEY BOX
NASH EDGERTON
JEREMY FRY
SETH DUHAMe
KATE BOYER
ALICE RIETVELD
EMILY BROBST
ZACK DUHAME
DALTON RONDELL
DAVID SCHULTZ
THOMAS STRUTHERS
MATT LEONARD